## Sheet1
Question | Option A | Option B | Option C | Option D | Correct Answer | Explanation | Domain | Task | Difficulty
Acosmetic company would liko to expand into tho pharmaceutical market: To assist in this, tho company acquiros an existing company that has ostablishod resourcos and experience operating in the pharmaceutical market_ The new pharmaceutical products involve higher levels of governance and stricter compliance regulations_While planning for a new pharmaceutical project the projecl manager realizes Ihat the majority of stakeholders and team members have worked on cosmelic projects in Ihe pasl bul only & few have experience with pharmaceutical projects; What should the project manager emphasize when identifying risks tor the project? | Fostering project team collaboration by facilitating meetings and teambuilding workshops | The compliance and regulatory risks associated with the pharmaceutical industry_ | Individuals who have worked on pharmaceutical projects should Iead the risk identification procoss. | Advocating for additional resources that have more experience with the pharmaceutical industry: | B | The compliance and regulatory risks associated with the new pharmaceutical product The project manager should emphasize the compliance and regulatory risks associated with the pharmaceutical industry when idenlifying risks for the projecl This is because the new pharmaceutical products involve higher levels of governance and stricter compliance regulations; which can pose significant risks t0 the project if not properly addressed It iS important t0 ensure that the team members and stakeholders are aware of these risks and take appropriate measures t0 mitigate them Other options are not as effective . Fostering project team collaboration is helpful in general, but may not directly address the importance of identifying compliance-related risks_ Advocating for additional resources or having individuals with pharmaceutical experience lead the risk identificalion process may be helpful but the compliance risks should be the primary focus and the entire team should be aware 0f lhe risks and participate in Ihe risk identification process | Process | Risk Management | Hard
What is the primary responsibility of a project manager? | To write detailed technical specifications | To manage project constraints and deliver value | To design system architecture | To perform quality assurance testing | B | Project managers are responsible for managing project constraints (scope, time, cost, quality, resources, and risk) and ensuring the project delivers value to stakeholders. | People | Project Leadership | Medium
Which process group includes the Close Project or Phase process? | Initiating Process Group | Planning Process Group | Executing Process Group | Closing Process Group | D | The Close Project or Phase process is part of the Closing Process Group and involves finalizing all activities across all process groups. | Process | Project Integration Management | Easy
What is the purpose of a stakeholder register? | To track project budget and expenses | To identify and document stakeholder information and engagement strategies | To schedule team meetings and workshops | To allocate human resources to tasks | B | The stakeholder register identifies and documents relevant information about project stakeholders, including their interests, involvement levels, and engagement strategies. | People | Stakeholder Engagement | Medium
Which document formally authorizes a project? | Project Management Plan | Statement of Work | Project Charter | Business Case | C | The project charter is the document that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources. | Process | Project Authorization | Easy
What is servant leadership in the context of project management? | Leading through authority and control | Leading by serving the team and removing obstacles | Leading through detailed micromanagement | Leading by delegating all responsibilities | B | Servant leadership focuses on serving the team members by removing obstacles, facilitating their work, and helping them achieve their potential. | People | Team Leadership | Hard
Which technique is used for schedule compression? | Resource smoothing | Fast tracking and crashing | Quality gate reviews | Risk register updates | B | Fast tracking (performing activities in parallel) and crashing (adding resources) are the two main schedule compression techniques. | Process | Schedule Management | Medium
What does RACI matrix stand for? | Resource Allocation and Control Index | Responsible, Accountable, Consulted, Informed | Risk Assessment and Communication Interface | Requirements Analysis and Change Integration | B | RACI matrix stands for Responsible (who does the work), Accountable (who signs off), Consulted (who provides input), and Informed (who is kept updated). | People | Team Management | Easy
Which organizational structure gives the project manager the most authority? | Functional Organization | Weak Matrix Organization | Projectized Organization | Strong Matrix Organization | C | In a projectized organization, the project manager has full authority over the project team and resources. | Business Environment | Organizational Structures | Medium
What is the purpose of the lessons learned register? | To track project costs and budget variances | To document knowledge gained during the project for future use | To schedule recurring team meetings | To manage project scope changes | B | The lessons learned register documents knowledge gained throughout the project that can be used to improve future project performance. | Process | Knowledge Management | Medium
Which is an example of an enterprise environmental factor? | Project charter | Work breakdown structure | Organizational culture and government regulations | Project management plan | C | Enterprise environmental factors include organizational culture, government regulations, market conditions, and other external factors that influence the project. | Business Environment | Environmental Factors | Medium
What is the difference between leads and lags in project scheduling? | Leads accelerate successor activities, lags delay them | Leads delay successor activities, lags accelerate them | Both leads and lags delay activities | There is no difference between leads and lags | A | A lead allows a successor activity to begin before its predecessor is complete, while a lag requires a delay between activities. | Process | Schedule Development | Hard
Which conflict resolution technique provides a temporary solution? | Confronting/Problem-solving | Compromising | Forcing/Directing | Collaborating | C | Forcing provides a temporary solution by pushing one viewpoint at the expense of others, often creating win-lose situations. | People | Conflict Management | Medium
What is the purpose of quality metrics in project management? | To measure and track project performance against quality objectives | To define the project scope boundaries | To control project schedule deviations | To manage stakeholder communications | A | Quality metrics are operational definitions that describe project or product attributes and how the control quality process will measure them. | Process | Quality Management | Medium
Which is an example of an organizational process asset? | Market conditions and competitive landscape | Government regulations and industry standards | Company policies, procedures, and historical information | Economic conditions and geographic factors | C | Organizational process assets include company policies, procedures, templates, historical information, and lessons learned from previous projects. | Business Environment | Organizational Assets | Easy
What is the primary focus of project risk management? | Eliminating all project risks completely | Maximizing positive risks (opportunities) and minimizing negative risks (threats) | Avoiding project execution altogether | Increasing project scope to accommodate risks | B | Risk management aims to maximize the probability and impact of positive events (opportunities) and minimize the probability and impact of negative events (threats). | Process | Risk Management | Medium
Which communication method is most effective for conveying complex information? | Email with attachments | Interactive face-to-face communication | Text messaging | Voice mail messages | B | Interactive face-to-face communication is most effective for complex information because it allows for immediate feedback, clarification, and non-verbal communication. | People | Communication Management | Medium
What are the three components of the triple constraint (traditional)? | Time, cost, and quality | Scope, time, and cost | Risk, quality, and scope | Resources, budget, and schedule | B | The traditional triple constraint consists of scope (what work will be done), time (when the work will be completed), and cost (how much the work will cost). | Process | Project Constraints | Easy
What is the purpose of Earned Value Management (EVM)? | To track team member performance ratings | To measure project performance by comparing planned work, completed work, and costs | To manage stakeholder expectations only | To control project risks and issues | B | EVM integrates scope, schedule, and cost measures to assess project performance by comparing the amount of work planned with what is actually accomplished. | Process | Performance Measurement | Hard
Which tool is used to identify the critical path in a project schedule? | Gantt Chart | Network Diagram with CPM (Critical Path Method) | Resource Histogram | Responsibility Assignment Matrix | B | The Critical Path Method (CPM) using network diagrams calculates the longest path through the project, which determines the minimum project duration. | Process | Schedule Development | Hard
What is the main purpose of a project kickoff meeting? | To close the project and document lessons learned | To align team members and stakeholders on project objectives, roles, and expectations | To conduct detailed risk assessments | To finalize the project budget allocation | B | The kickoff meeting aligns all team members and stakeholders on project objectives, success criteria, roles, responsibilities, and expectations for the project. | People | Team Development | Easy